Shooting Schedule

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Day and Date | Time | Location | Cast required | Crew required | Scene name | Shooting reviewed and complete |
| Tuesday 23rd April |  | House | Alexis | Myself | Test shots | Completed |
| Friday 26th | Afternoon | House | Alexis | Myself | Waking up scene  Going down the stairs into the kitchen  Lays down on the sofa | Completed |
| Monday 29th | 8:30-4 | House | Alexis | Myself | Goes back into the kitchen  Sits down gets the text message  Sits down on the sofa turns the tv on  Laying in bed doing work  Listening to music  Replies to the text message  ENDING | Completed |

After creating a schedule I was unable to stick to this due to the test shots and other pre-production paperwork and the time it took to film was longer than expected. This then meant that I was more pushed for time and had to start filming the test shots on the Wednesday instead due to the pre-production paperwork taking longer than expected and I had to finish of the editing for this on the Friday meaning I wasn’t able to get as much filming done on the Friday for my final video. This then had a knock on effect and meant that I had to then film more on the Monday meaning that I ended up finishing filming on the Tuesday, rather than on the Monday which was scheduled. I decided to tweak my schedule slightly so that I it is going to be more realistic for me to achieve. Below you can see another table which shows the changes that I have made so that I can get the work done. Now that I have created this other schedule I am going to have to make sure that I stick to it so that I have enough time to edit the footage ready for the deadline.

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Day and Date | Time | Location | Cast required | Crew required | Scene name | Shooting reviewed and complete |
| Tuesday 23rd April |  | House | Alexis | Myself | Test shots | Completed |
| Friday 26th | Afternoon | House | Alexis | Myself | Test shots  Waking up scene | Completed |
| Monday 29th | 8:30-4 | House | Alexis | Myself | Going down the stairs into the kitchen  Lays down on the sofa  Goes back into the kitchen  Sits down gets the text message  Sits down on the sofa turns the tv on  Laying in bed doing work | Completed |
| Tuesday 30th | 9-12 | House | Alexis | Myself | Listening to music  Replies to the text message  ENDING | Completed |